## Sheet1
Difficulties: 1:simple view action 2:simple db manipulation 3:complex db manipulation 4:complex db manipulation + complex logic manipulation 5:other hard stuff +0.5: if long CRUD operation
Roles: 1-Visitor 2-User 3-Service provider 4- Admin 5- facebook Bot
Visitor | [7 empty] | Sprint 1 |  |  | Sprint 2 |  |  | Sprint 3
ID | STORY / FEATURE / REQUEST | Dependency | Story Points | Priority | Status | Success Demos | Failure Demos | Members | Status | Difficulty | Members | Status | Tested |  | Status
1.1 | As a visitor, I can explore new activities to find new activities. | none | Med | 2 | not started | trending activties are retrieved and displayed | -if no activties are available, appropriate message should be. | Wassim & Mairam | Done | 2 | Wassim & Mairam | yes | yes |  | -
1.2 | As a visitor, I can view detailed information about service providers to be able to contact them. | none | Easy | 2 | not started | service provider data displayed to the visitor | none | Andrea & Kareem | Done | 2 | Andrea & Karim | yes | no |  | Yes
1.3 | As a visitor I can filter activities by prices, offers, locations, themes or reviews/ratings to find activities i want | none | Hard | 4 | not started | visitor is moved a page including different activities in different entertainment fields according to his filter option | none | Wassim & Mairam | Done | 3 | Wassim & Mairam | yes | yes |  | -
1.4 | As a visitor, I can register so that I can have an account and many user privileges. | visitor should have an active email | Med | 1 | not started | confirmation message after successful registration | -visitor doesn't provide any of the manadatory attributes -username already exists -password doesn't meet the requirements | Andrea & Kareem | Done | 3 | Sherrie & Youssef | yes | yes |  | -
1.5 | As a visitor, I can search for activities either by name or type or date to find certain activities directly. | none | Hard | 3 | not started | visitor is movedto a page including activities following his search criteria | visitor does not find the activities he searched for, a message is displayed notifying the visitor | Michael Reda & Michael Morcos | Done | 3 | Michael & Michael | yes | yes |  | -
1.6 | As a visitor I can read about the platform through the “about us” option to find out about the platform. | none | Easy | 3 | not started | visitor is moved to a page including the information about the platform | none | Wassim & Mairam | Done | 1 | Wassim & Mairam | yes | yes |  | -
1.7 | As a visitor I can have access to a FAQ page to get quick answers to obvious questions. | none | Med | 4 | not started | visitor is moved to a page including the frequently asked questions on our platform | none | andrea & Kareem | Done | 1 | Andrea & Karim | yes | yes |  | -
1.8 | As a visitor I can Sign up for a weekly newsletter to get new offers weekly. | none | Med | 4 | not started | visitor is moved to a page including information about the platform | -invalid email address is entered -email already signed up | Sherry & Youssef | Done | 3 | Sherrie & Youssef | yes | no |  | Yes
1.9 | As a visitor I can share offers on social media to tell my friends about offers i like. | visitor finds an activity that he/she likes | Hard | 3 | not started | visitor is moved to a page to choose the social media he/she will share on | -none | Michael Reda & Michael Morcos | Done | 4.5 | Michael & Michael | yes | yes |  | -
1.11 | As a visitor I can Apply as a Service Provider to offer my activities on the platform | provide legal document, doesn't already have an account | Med | 1 | not started | confirmation message then he/she is redirected to their page | missing or wrong inputs message | Wassim & Mairam | Done | 3 | Sherrie & Youssef | yes | yes |  | -
User
ID | STORY / FEATURE / REQUEST | Dependency | Story Points | Priority | Status | Success Demos | Failure Demos
2.1 | As a user I can login to access my account | Registered | Easy | 1 | not started | Hame page Loaded -"Logged in successfully" message | missing or wrong inputs message | Sherry & Youssef | Done | 3.5 | Sherrie & Youssef | yes | yes |  | -
2.2 | As a logged in user I can view and update my personal info | Logged in | Easy | 4 | not started | view Acount information |  | Michael reda & Michael Morcos | Done | 2 | Michael & Michael | yes | yes |  | -
2.3 | As a logged in user I can rate/review activities after check-in | Logged in - checked in this activity at least once | Easy | 3 | not started | "Rating is posted successfully" message | "invalid rating" message | Michael reda & Michael Morcos | Done | 3.5 | Michael & Michael | yes | yes |  | -
2.4 | As a logged in user I can subscribe to service providers so that i can receive offers and promotions | Logged in | Easy | 3 | not started | subscription status is updated to subscribed -"suscibed successfully" message | some certain providers accept subscibers above a certain age pertaining to the nature of the service, corresponding error message is displayed | Sherry & Youssef | Done | 2 | Andrea & Karim | yes | no |  | NO
2.5 | As a logged in user I can submit my interests so that i can find close activities to my liking | Logged in | Med | 2 | not started | "interest saved to system" message |  | Wassem & Mariam | Done | 2.5 | Sherrie & Youssef | yes | yes |  | -
2.6 | As a logged in user I can compare different providers together or different activities by their attributes | Logged in | Med | 2 | not started | comparison data recived and displayed | - user did not choose two parties error message | Wassem & Mariam | Done | 4 | Wassim & Mairam | yes | yes |  | -
2.7 | As a logged in user I can reserve a booking for an activity by payment | Logged in | Hard | 2 | not started | user redirected to payment page - a successful message is displayed -booking inserted in user history | -user age is inappropriate for activity error message -reservation timing is already booked -invalid payment details | Sherry & Youssef | Done | 5.5 | Michael Reda & Youssef | yes | yes |  | -
2.8 | As a logged in user I can submit a complaint in service provider | Logged in - already checked in with provider and within 3 days of checking in | Med | 3 | not started | "complaint successfully posted" message | -user did not check in to issue complaint error message -user left complaint field empty error message -after 3 days of checking in error message | Wassem & Mariam | Done | 2 | Wassim & Mairam | yes | yes |  | -
2.9 | As a logged in user I can view my history bookings and reservations | Logged in | Med | 4 | not started | user redirected to page containing history | - user does not have activities in history error message | Michael reda & Michael Morcos | Done | 1 | Michael & Michael | yes | yes |  | -
2.11 | As a logged in user I can add (or drop)activities to my wish-list so that i get notified whenever there are promotions and offers. | Logged in | Med | 3 | not started | wish list status is updated to added -"wish added successfully" message | "duplicate wish " message | Andrea & Karim | Done | 2 | Andrea & Karim | yes | yes
2.12 | As a logged in user I can change my privacy to control who sees my information | Logged in | Easy | 4 | not started | privacy settings successfully changed | user choose same settings sarcastic error message | Michael reda & Michael Morcos | Done | 2 | Andrea & Karim | yes | yes |  | -
2.13 | As a logged in user I can send gifts to other users | Logged in | Hard | 3 | not started | user redirected to payment page - a successful message is displayed -booking inserted in gift reciever's notifications | -invalid gift receiver username error message -gift receiver's age is inappropriate for activity erro message -reservation timing is already booked -invalid payment details | Michael reda & Michael Morcos | Done | 5 | Michael & Michael | view only | no |  | No
2.14 | As a logged in user I can contact the platform to negotiate grave problems | Logged in | Med | 3 | not started | "message delivered successfully" message | -message body emty error message -exceeded number of charachters error message | Sherry & Youssef | Done | 2 | Sherrie & Youssef | yes | no |  | Yes
Service Provider
ID | STORY / FEATURE / REQUEST | Dependency | Story Points | Priority | Status | Success Demos | Failure Demos
3.1 | As a service provider, I shall login with my firm’s credentials so that I can manage my page with all of its details. i.e. use all of the platform features. | Regesterd and approved | Easy | 1 | not started | "Logged in successfully" message | missing or wrong inputs message | Wassem & Mariam | Done | 2 | Sherrie & Youssef | yes | yes |  | -
3.2 | As a service provider I shall add activities that my firm provides so that I can schedule them for my clients. | Logged in | Hard | 2 | not started | "activity added successfully" message - the activity appears in service provider page | missing or wrong inputs message | Sherry & Youssef | Done | 3.5 | Sherrie & Youssef | yes | yes |  | -
3.3 | As a service provider, I shall be able to add offers and promotions. | Logged in | Hard | 2 | not started | "Package/offer added successfully" message - the offer appears for the target clients | missing or wrong inputs message | Andrea & Kareem | Done | 2.5 | Andrea & Karim | yes | no |  | NO
3.4 | As a service provider, I may promote to my history clients. i.e. on their birthday. | Logged in - there are history clients | Hard | 3 | not started | target clients are notified that they have been promoted - confirmation message | missing or wrong inputs message | Andrea & Kareem | Done | 3 | Andrea & Karim | no | no |  | NO
3.5 | As a service provider, I shall keep track of holding reservations before 24 hours of the booking timing. | Logged in | Easy | 3 | not started | page with all reservations displayed | "no reservations made" message | Andrea & Kareem | Done | 4 | Andrea & Karim | no | no |  | NO
3.6 | As a service provider, I shall confirm booked user check-ins so that I can consider them clients to me. | logged in | Easy | 3 | not started | " thanks for visiting" email to client -"confrimed successfully" message for provider | "no booked activity" message | Sherry & Youssef | Done | 4 | Andrea & Karim | yes | no |  | NO
3.7 | As a service provider, I may apply for a Golden Service Provider package so that I can get more advertisement space on the platform. | Logged in -has Rating >3.5 | Med | 4 | not started | "you have been upgraded to golden" mesage | - "already a golden member" message -"no sufficient funds" message -"rating less than required" message | Andrea & Kareem | Done | 2 | Andrea & Karim | view only | yes |  | -
Admin
ID | STORY / FEATURE / REQUEST | Dependency | Story Points | Priority | Status | Success Demos | Failure Demos
4.1 | As an admin, I can login so that I can manage the system. | access link known | Easy | 1 | not started | "Logged in successfully" message | missing or wrong inputs message | Michael Reda & Michael Morcos | Done | 2 | Sherrie & Youssef | yes | no |  | Yes
4.2 | As an admin, I can view service providers requests in order to accept or refuse them. | Logged in | Easy | 2 | not started | redirected to page containing all service provider requests | -"no current service provider requests" | Michael Reda & Michael Morcos | Done | 3 | Michael & Michael | yes | yes |  | -
4.3 | As an admin, I can view complains in order to Improve the service (website) | Logged in | Easy | 3 | not started | redirected to page containing all complaints | -"no current complaints" message | Michael Reda & Michael Morcos | Done | 2.5 | Wassim & Mairam | yes | yes |  | -
4.4 | As an admin, I can logout so that no one can manage the system except the admin. | Logged in | Easy | 1 | not started | redirected to home page |  | Sherry & Youssef | Done | 1 | Sherrie & Youssef | yes | yes |  | -
4.5 | As an admin, I can view logs to improve my system. | Logged in | Easy | 3 | not started | redirected to page with all system logs | -"no current logs" message | Sherry & Youssef | Done | 2.5 | Sherrie & Youssef | yes | no |  | Yes
4.6 | As an admin, I can update the ban status of any user service provider | Logged in | Med | 3 | not started | "Banned successfully" message | -no service provider or user to be banned error message -user or service provider is already banned | Sherry & Youssef | Done | 2 | Sherrie & Youssef | no | no |  | No
4.7 | As an admin, I can view the user contact message, to be able to display it and read it. | Logged in | Easy | 4 | not started | redirect to page containing all user contact messages | "no current user messages" message | Andrea & Kareem | Done | 2 | Andrea & Karim | yes | yes |  | -
4.8 | As an admin, I can view analytics, to be updated with all analytics of the platform. | logged in | Hard | 4 | not started | redirected to a page that has analytics about different aspects of the platform |  | Wassem & Mariam | Done | 1 | Wassim & Mairam | yes | yes |  | -
facebook bot
ID | STORY / FEATURE / REQUEST | Dependency | Story Points | Priority | Status | Success Demos | Failure Demos
5.1 | As a Facebook bot, I can respond to questions asked by the user. | user is logged in to facebook | Hard | 4 | not started | user facebook messenger receives a question | none | - | Not Done | 5.5 | - | no | no |  | Yes
5.2 | As a Facebook bot, I can offer the user several options for choosing between them to display certain information without asking or answering questions. | user is logged in to facebook | Hard | 4 | not started | user facebook messenger receives an answer | bot doesn't understand a question asked by the user; error message -an ambiguous question that has multiple answers; error message | - | Not Done | 5.5 | - | no | no |  | Yes
5.3 | As a Facebook bot, I can ask questions to the user. | user is logged in to facebook | Hard | 4 | not started | display a list of information per chosen option for the user | none | - | Not Done | 5.5 | - | no | no |  | Yes